## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 38
PROJECT NAME | Offline Data Collection and Cleaning App for Development Projects
PROJECT MENTOR (sponsor) | Anusandhan Social Consultants LLP
TEAM MEMBERS | Vishesh Saraswat
Harshikaa Agrawal
Kushal Balabhadruni
Sriyansh Suryadevara
Aishita Marri

## Status
38
PROJECT NAME | Offline Data Collection and Cleaning App for Development Projects
PROJECT MENTOR (sponsor) | Anusandhan Social Consultants LLP
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Harshikaa | 0.5 | 0.5 | Done |  | 0 | 0
GIT Repository setup | Preparation | Kushal | 1 | 2 | Ongoing |  | -1 | 50
Client meeting | Coordination | Aishita | 1 | 4 | Done | Difficulty in fixing a time | -3 | 75
Deciding potential tech stacks | Preparation | Harshikaa | 2 | 2 | Done |  | 0 | 0
Project synopsis writeup | Documentation | Vishesh | 2 | 2 | Ongoing |  | 0 | 0
Identify role owners | Preparation | Vishesh | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Sriyansh | 2 | 2 | Done |  | 0 | 0
Develop questions for requirements elicitation | Documentation | Kushal | 1.5 | 1.5 | Done |  | 0 | 0
Status tracker | Documentation | Sriyansh | 1.5 | 1.5 | Done |  | 0 | 0
Week 2 (January 22 - January 28)
Learn about flutter | Preparation | Harshikaa | 1 | 2 | Done |  | -1 | 50
Learn about react-native | Preparation | Vishesh | 1 | 2 | Done
Decide between flutter and react-native | Preparation | Kushal | 1.5 | 1.5 | Done
GIT Repository setup | Preparation | Harshikaa | 2 | 1 | Done |  | 1 | 100
Team Meeting | Coordination | Vishesh | 2 | 1 | Done |  | 1 | 100
Status tracker | Documentation | Kushal | 1 | 1 | Done |  | 0 | 0
Looked at Google Forms and Microsoft Forms | Preparation | Aishita | 2 | 2 | Done |  | 0 | 0
Looked at Surveycto and KoboToolbox | Preparation | Sriyansh | 2 | 2 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
Learn about React.js | Preparation | Vishesh | 2 | 2 | Done |  | 0 | 0
Learn about Express.js and Node.js | Preparation | Aishita | 1.5 | 1.5 | Done |  | 0 | 0
Learn about MongoDB | Preparation | Kushal | 1 | 1 | Done |  | 0 | 0
Setup MongoDB Account for testing | Preparation | Kushal | 1 | 1 | Done |  | 0 | 0
Figma design for app | Design | Harshikaa | 2 | 2 | Done |  | 0 | 0
Figma design for dashboard | Design | Sriyansh | 2 | 2 | Done
High level architecture design | Documentation | Aishita | 1.5 | 1.5 | Done
Schedule meeting with client | Coordination | Vishesh | 0.5 | 0.5 | Done
Team Meeting | Coordination | Sriyansh | 2 | 2 | Done
Client Meeting | Coordination | Kushal | 1 |  | Done
Week 4 (February 5 - February 11)
Setting up development enviroment | Preparation | Harshikaa | 1.5 | 2 | Done |  | -0.5 | 25
Home Page of mobile application | Development | Vishesh | 2 | 2 | Done |  | 0 | 0
Form UI | Development | Sriyansh | 2 | 3 | Done
UI for available forms to download | Development | Harshikaa | 2 | 2 | Done
UI for saving forms | Development | Aishita | 2 | 2.5 | Done
UI for available forms for fill | Development | Kushal | 2 | 2.5 | Done
Team Meeting | Coordination | Kushal | 1 | 1.5 | Done
Client Meeting | Coordination | Aishita | 1 | 1 | Done
Fix meeting with client | Coordination | Vishesh | 1 | 0.5 | Done
Week 5 (February 12 - February 19)
SRS Document Overview | Requirements | Harshikaa | 1 | 1 | Done
SRS Document Use Case Diagram | Requirements | Sriyansh | 1 | 1 | Done |  | 0 | 0
SRS Document Use Case Description 1-2 | Requirements | Vishesh | 1 | 1.5 | Done |  | -0.5 | 33.3333
SRS Document Use Case Description 3-4 | Requirements | Sriyansh | 1 | 1 | Done
SRS Document Use Case Description 5-6 | Requirements | Aishita | 1 | 1.5 | Done
Skip Logic Functionality in App | Development | Kushal | 2 | 2.5 | Done |  | -0.5 | 20
JSON format for forms | Design | Harshikaa | 1 | 1 | Done
Feature to save progress on forms | Development | Aishita | 1 | 1.5 | Done
Show and edit saved forms | Development | Vishesh | 1 | 1 | Done
Display completed forms available for upload | Development | Sriyansh | 1 | 1 | Done
Team Meeting | Coordination | Harshikaa | 1 | 1 | Done
Client Meeting | Coordination | Kushal | 0.5 | 0.5 | Done
Fix Meeting with Client | Coordination | Vishesh | 0.5 | 0.5 | Done
Week 6 -7(February 20 - March 5)
Fixed issues with fill forms page | Development | Harshikaa | 1 | 1 | Done
Modified skip logic for simplicity | Design | Kushal | 1 | 1.5 | Done
Decided on the Excel sheet format | Development | Vishesh | 1 | 1.5 | Done
Fixed Edit forms issue with stored questions | Development | Sriyansh | 0.5 | 1 | Done |  | -0.5 | 50
Converting Excel to Json format | Development | Kushal | 2 | 2 | Done |  | 0 | 0
Deciding DB Schema for users | Design | Vishesh | 1 | 1 | Done |  | 0 | 0
Deciding DB Schema for Forms | Design | Harshikaa | 1 | 1 | Done |  | 0 | 0
Setup Backend | Development | Aishita | 1 | 1 | Done |  | 0 | 0
Setup MongoDB for Forms | Preparation | Vishesh | 1 | 1 | Done |  | 0 | 0
Setup basic web dashboard | Development | Aishita | 1 | 1 | Done |  | 0 | 0
Added Delete option in Edit forms page | Development | Harshikaa | 0.5 | 1 | Done |  | -0.5 | 50
Team Meeting | Coordination | Sriyansh | 1.5 | 1.5 | Done |  | 0 | 0
Client Meeting | Coordination | Vishesh | 0.5 | 0.5 | Done |  | 0 | 0
Fix Meeting with Client | Coordination | Sriyansh | 0.5 | 0.5 | Done |  | 0 | 0
Week 6 -7(March 6 - March 12)
Integrated Backend and mobile application | Development | Harshikaa | 1 | 1 | Done |  | 0 | 0
Created Template for form creation | Design | Kushal | 2 | 2 | Done |  | 0 | 0
Made the template downloadable from web dashboard | Development | Kushal | 1 | 1 | Done |  | 0 | 0
Cleaned the codebase (maintaining a single ID for forms) | Development | Sriyansh | 1.5 | 1 | Done |  | 0.5 | 50
Added a backend route for sync | Development | Vishesh | 1 | 1 | Done |  | 0 | 0
Deciding DB Schema for Responses | Design | Harshikaa | 1 | 1 | Done |  | 0 | 0
Added a backend route to download responses of a form | Development | Aishita | 1 | 1 | Done
Design for responses web interface | Design | Aishita | 1 | 1 | Done |  | 0 | 0
Implemented sync functionality on the application | Development | Vishesh | 1 | 1 | Done |  | 0 | 0
Setup Backend | Development | Aishita | 1 | 1 | Done |  | 0 | 0
Fix Meeting with Client | Coordination | Sriyansh | 0.5 | 0.5 | Done |  | 0 | 0
Week 6 -7(March 13 - March 19)
Implemented web interface for downloading responses | Development | Aishita | 1.5 | 2 | Done |  | -0.5 | 25
Fixed issues with template | Development | Kushal | 1 | 1.5 | Done |  | -0.5 | 33.3333
Refactor to allow for mobile to laptop communication | Development | Sriyansh | 1 | 1.5 | Done |  | -0.5 | 33.3333
Modify the SRS document to reflect changes in project | Development | Kushal | 1 | 1 | Done |  | 0 | 0
Modify the Project plan document to reflect changes | Design | Vishesh | 1 | 1 | Done |  | 0 | 0
Modify the Synopsis document to reflect changes | Design | Sriyansh | 1 | 1 | Done |  | 0 | 0
Created Presentation | Development | Harshikaa | 2.5 | 3 | Done |  | -0.5 | 16.6667
Made a demo of the project | Documentation | Vishesh | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Kushal | 2 | 2 | Done |  | 0 | 0
Client Meeting | Coordination | Aishita | 1 | 1.5 | Done |  | -0.5 | 33.3333
Fix Meeting with Client | Coordination | Sriyansh | 0.5 | 0.5 | Done |  | 0 | 0
Week 7-8(March 19 - March 25)
Filtering Responses - UI/UX | Design | Vishesh | 1.5 | 2 | Done |  | -0.5 | 25
Filter responses based on Selected Answers | Development | Harshikaa | 2 | 3 | Done |  | -1 | 33.3333
Functionality to hide columns with no responses | Development | Kushal | 1 | 1.5 | Done
Modified template to add sections to forms | Design | Sriyansh | 1 | 1 | Done |  | 0 | 0
Added questions with multi option picking | Development | Aishita | 1 | 1 | Done |  | 0 | 0
Added question type with range answer | Development | Vishesh | 1 | 1 | Done |  | 0 | 0
Added rest of the question types | Development | Vishesh | 1 | 1.5 | Done |  | -0.5 | 33.3333
Frontend Modifications for new question types on mobile | Design | Kushal | 2 | 1.5 | Done |  | 0.5 | 33.3333
Backend changes to support new question types | Development | Sriyansh | 2 | 2 | Done |  | 0 | 0
Modified template to include new question types | Design | Harshikaa | 0.5 | 0.5 | Done
Client Meeting | Coordination | Aishita | 1 | 1 | Done |  | 0 | 0
Fix Meeting With Client | Coordination | Sriyansh | 0.5 | 0.5 | Done |  | 0 | 0
Week 8-9(March 26 - April 2)
Created User Model | Design | Aishita | 0.5 | 0.5 | Done
Added Backend routes for User | Development | Kushal | 2 | 2 | Done
Testing the backend routes with Postman | Testing | Sriyansh | 1 | 1 | Done
Created Login Page on mobile app | Development | Kushal | 1 | 1 | Done
Created Sign up page on mobile app | Development | Vishesh | 1 | 1 | Done
Added functionality to store tokens on app | Development | Harshikaa | 1 | 1 | Done
Added Logout Functionality | Development | Aishita | 0.5 | 0.5 | Done
Fixed Issues in the mobile app authentication | Development | Vishesh | 1 | 2 | Done
Modified parsing of excel to include new question types | Development | Harshikaa | 1 | 1 | Done
Modified parsing of excel to include sections for each question | Development | Aishita | 1 | 1.5 | Done
Testing Plan | Testing | Sriyansh | 1.5 | 2 | Done |  | -0.5 | 25
Team Meeting | Coordination | Harshikaa | 1 | 1 | Done
Week 9-10 (April 2 - April8)
Web Dashboard Auth cookies - Backend Token generation and maintenance | Development | Sriyansh | 2 | 2 | Done |  | 0 | 0
Web Dashboard Cookies - Frontend AuthContextSetup | Development | Kushal | 2 | 2 | Done
Resolving CORS Issues | Development | Kushal | 1 | 1 | Done
User Sign up Frontend | Interfaces | Vishesh | 1 | 1 | Done
User login Frontend | Interfaces | Harshika | 2 | 2 | Done |  | 0 | 0
Modify backend routes to fetch forms created by user only | Development | Vishesh | 1 | 1 | Done
Modify to fetch repsones to only forms created by user | Development | Vishesh | 1 | 1 | Done |  | 0 | 0
Functionality to grant access of forms to certain users | Development | Sriyansh | 1 | 1 | Done |  | 0 | 0
UI for granting access | Interfaces | Aishitha | 2 | 2 | Done |  | 0 | 0
Explore FIle options for large media on mobile | Preparation | Aishitha | 1 | 1 | Done |  | 0 | 0
Learn Expo FIle System | Preparation | Harshika | 1 | 1 | Done |  | 0 | 0
Week 10-11 (April 8 - April 14)
UI Plan for Data Visualisation Components | Design | Aishitha | 1 | 1 | Done |  | 0 | 0
Implementing logic for Data Visualization | Development | Harshika | 1 | 2 | Done |  | -1 | 50
Pie Charts for MCQs | Preparation | Harshika | 1 | 1 | Done |  | 0 | 0
Line Chart | Development | Sriyansh | 1 | 1 | Done |  | 0 | 0
Word Cloud Implementation | Development | Kushal | 1 | 1 | Done |  | 0 | 0
Media Upload Planning | Design | Sriyansh | 1 | 2 | Done |  | -1 | 50
Setting up File Routes | Development | Kushal | 1 | 2 | Done
Enabling Media Upload to backend | Development | Aishitha | 1 | 2 | Done |  | -1 | 50
Media Upload Button | Development | Aishitha | 1 | 1 | Done |  | 0 | 0
Apply Filters to Visualised Data | Development | Harshika | 1 | 1 | Done |  | 0 | 0
Record Audio Functionality | Development | Vishesh | 1.5 | 2 | Done |  | -0.5 | 25
Continue audio from where it was stopped | Development | Vishesh | 1 | 1.5 | Done |  | -0.5 | 33.3333

## Sheet1
Weekly Targets
1 | have a plan + design to show
2 | app without skipping logic and offline thing (data collection)
3 | app refined with requirements
4 | exporting without empty columns
5 | simple interface to create forms
6 | improve interface to make it intuitive
7 | add dashboard for visualisation
8 | role based verification/authentication
9 | integration of everything and testing
10 | fix issues
11 | deployment
12 | additional stuff